## Project Planner
Project Sprinkler
Hazera Seeds BV, Project Sprinkler |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START week | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Permit municipality | 9 | 8 | 5 | 13 | 100%
Dismantle Silo | 5 | 1 | 5 | 1 | 100%
Extra Sondering Konings sonderingen Roosendaal | 7 | 1 | 7 | 1 | 100%
Acheologic report findings ready | 6 | 1 | 6 | 1 | 100%
Start building pumphouse | 27 | 15 | 27 | 0 | 15%
Engeneer sprinkler start | 12 | 6 | 12 | 5 | 100%
Sprinkler Treshing shed | 26 | 1 | 26/30 |  | 0%
Sprinkler Portakabin | 30 | 1 | 30 |  | 0%
Sprinkler warehouse | 31 | 7 |  |  | 0%
Ceiling Offices out Weekend (4 sept) | 36 | 1 |  |  | 0%
Sprinkler offices | 38 | 2 |  |  | 0%
Obstruction several area's |  |  |  |  | 0%
Greenhouse supporting | 35 | 2 |  |  | 0%
Sprinkler greenhouse | 39 | 6 |  |  | 0%
Pumphouse installation | 0 | 0 |  |  | 0%
Start placing pump | 0 | 0 | 0 | 0 | 0%
Activity 10 | 0 | 0 | 0 | 0 | 0%
Activity 11 | 0 | 0 | 0 | 0 | 0%
Activity 12 | 0 | 0 | 0 | 0 | 0%
Activity 13 | 0 | 0 | 0 | 0 | 0%
Activity 14 | 0 | 0 | 0 | 0 | 0%
Activity 15 | 0 | 0 | 0 | 0 | 0%
Activity 16 | 0 | 0 | 0 | 0 | 0%
Activity 17 | 0 | 0 | 0 | 0 | 0%
Activity 18 | 0 | 0 | 0 | 0 | 0%
Activity 19 | 0 | 0 | 0 | 0 | 0%
Activity 20 | 0 | 0 | 0 | 0 | 0%
Activity 21 | 0 | 0 | 0 | 0 | 0%
Activity 22 | 0 | 0 | 0 | 0 | 0%
Activity 23 | 0 | 0 | 0 | 0 | 0%
Activity 24 | 0 | 0 | 0 | 0 | 0%
Activity 25 | 0 | 0 | 0 | 0 | 0%
Activity 26 | 0 | 0 | 0 | 0 | 0%

## Pomphuis
Project Planner Pomphuis
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Inrichten bouwterrein | 28 | 1 | 28 | 0 | 0%
Grond/sloopwerk | 28 | 1 | 0 | 0 | 0%
Maatvoering | 28 | 2 | 0 | 0 | 0%
Aanbrengen Heipalen | 29 | 1 | 0 | 0 | 0%
Doormeten Palen | 30 | 3 | 0 | 0 | 0%
Instort voorziening | 30 | 1 | 0 | 0 | 0%
Herstel Grondpakket | 30 | 2 | 0 | 0 | 0%
Koppensnellen | 34 | 5 | 0 | 0 | 0%
Slaan bruggetjes | 34 | 1 | 0 | 0 | 0%
Werkvloer (beton) | 34 | 6 | 0 | 0 | 0%
Bekisting | 35 | 2 | 0 | 0 | 0%
Bewapening | 35 | 2 | 0 | 0 | 0%
Aarding | 36 | 1 | 0 | 0 | 0%
Betonvloer monolitisch | 36 | 1 | 0 | 0 | 0%
Ontkisten (na 4 weken) | 37 | 1 | 0 | 0 | 0%
Bekisting Fase 2 | 37 | 1 | 0 | 0 | 0%
Isoleren vloer (pomphuis) | 37 | 1 | 0 | 0 | 0%
Wapening | 37 | 2 | 0 | 0 | 0%
Storten vloer pomphuis | 38 | 1 | 0 | 0 | 0%
Bekisting Fase 3 | 38 | 1 | 0 | 0 | 0%
Wapening (stort gereed maken) | 38 | 1 | 0 | 0 | 0%
Storten opstort | 39 | 1 | 0 | 0 | 0%
Maatvoering/ stelwerk | 39 | 1 | 0 | 0 | 0%
Waterkerende laag | 39 | 1 | 0 | 0 | 0%
Lijmwerk binnenblad | 39 | 2 | 0 | 0 | 0%
Steigers rondom | 40 | 1 | 0 | 0 | 0%
Leggen dakplaten | 40 | 1 | 0 | 0 | 0%
Afstorten naden | 40 | 1 | 0 | 0 | 0%
Stelwerk buitenblad | 40 | 1 | 0 | 0 | 0%
Stelkozijnen +waterkering | 41 | 1 | 0 | 0 | 0%
Houten rekwerk op dak | 41 | 1 | 0 | 0 | 0%
Gevel metselwerk+isolatie | 41 | 2 | 0 | 0 | 0%
Voegwerk | 43 | 1 | 0 | 0 | 0%
Plaasten deurkozijn | 43 | 1 | 0 | 0 | 0%
Dakbedekking | 42 | 1 | 0 | 0 | 0%
Aanbrengen dakkappen | 43 | 1 | 0 | 0 | 0%
HWH's aansluiten/ overstort | 43 | 1 | 0 | 0 | 0%
Afwerken pomphuis | 43 | 1 | 0 | 0 | 0%
Installaties pomphuis | 43 | 2 | 0 | 0 | 0%
Afwerken terrein bestrating | 44 | 1 | 0 | 0 | 0%
Opleveren bouwkundig | 44 | 1 | 0 | 0 | 0%